## Slide 1: Tentative FSAP Milestone
AML/CFT Working Group

## Slide 2
Tentative FSAP Milestone
Present
Pre-FSAP
1. Agreement of the scoping
2. Confidentiality protocols
12-14 Jul 2006
1st Mission
2nd Mission
Article IV
Mission
Board discussion
Jan
2007
May 2006
Apr
2007
Jun
2007
Sep
2007
Receive Questionnaire
Late Jul – early Aug
1. Names of the Assessors are identified
2. Agreement on mission date
Participating country:
- Write comment on detail assessment/ ROSC
- Run stress test
Send the assessment report to IMF for review
IMF sends feedback to BOT
Output:
- Detail assessment
- Summary ROSC
Write Aide Mémoire (AM)
Return completed AM to BOT
Wrap up
Additional:
FSAP Mission staffs discuss with the BOT to complete AM
Fund staff members prepare on FSSA as background to Article IV Board Mission
Bank staff members prepare FSA to inform bank board and to highlight key structural and developmental issues
Agreement of Pre-FSAP
Submit:
1. Pre-conditions
2. Background notes on financial sector
Submit:
- Self-assessment
Discussion of detailed standards assessments with BOT (typically through correspondences) to incorporate the authority’s response to staff assessments.
Transmission of technical notes and detailed standards assessments to BOT
Publication in line with agreed policies
Wrap up
Within 2 weeks
Within 2-3 mths.
Within 1 mth.
Return
Questionnaire